CE3208

Construction Materials and Methods

ASSIGNMENT NO. 1

Material Cost and Labor Cost Estimate

CHB Fence – Per Span/Bay

Prepared by: _________________________

Date: _______________________________

I. LIST OF ASSUMPTIONS

A. Structural Dimensions (From Drawing S-2)

| Item | Dimension | Remarks |
| --- | --- | --- |
| Bay/Span Width | 4,200 mm (4.20 m) | From drawing |
| Wall Height (above NGL) | 2,400 mm (2.40 m) | NGL to Apex |
| CHB Specification | 6" CHB (150x200x400mm) | Changed per Spec Item 5 |
| Footing Size (FC1) | 0.80 m x 1.30 m x 0.30 m | From Footing Schedule |
| Footing Embedment Depth | 600 mm (0.60 m) | Minimum per drawing |
| Bottom Bars X-axis | 7 pcs – 12mm dia. | From Footing Schedule |
| Bottom Bars Y-axis | 5 pcs – 12mm dia. | From Footing Schedule |
| Concrete Strength | fc' = 21 MPa (3000 psi) | Per drawing |

B. Lintel Beam Assumptions

Based on standard practice for CHB fences with 2.40m height, assume the lintel beam at the top of the wall:

| Item | Value | Basis |
| --- | --- | --- |
| Lintel Beam Size | 150mm x 200mm (6"x8") | Standard for 6" CHB |
| Lintel Beam Span | 4.20 m | = bay width |
| Reinforcement | 2-12mm dia. top & bottom | Standard practice |
| Stirrups | 10mm dia. @ 200mm O.C. | Standard practice |

C. Material & Wastage Assumptions

| Item | Wastage/Factor | Remarks |
| --- | --- | --- |
| CHB (6" blocks) | 5% wastage | Cutting & breakage |
| Cement – Mortar | 10% wastage | Spills & mixing |
| Sand – Mortar | 10% wastage | Spills & mixing |
| Cement – Concrete | 10% wastage | Mixing losses |
| Gravel – Concrete | 10% wastage | Mixing losses |
| Formworks | Re-use factor = 4 | Per assignment spec |
| Reinforcing Steel | 10% wastage+laps | Cutting & lapping |
| Plastering Mortar | 20mm thick, both sides | Per assignment spec |
| CHB Mortar Joint | 10mm bed joints | Standard practice |

D. Mix Design Assumptions – Site Mix 1:2:3 (3000 psi)

Using DPWH Blue Book / standard proportions for 1:2:3 mix:

| Component | Quantity per m³ concrete | Unit |
| --- | --- | --- |
| Portland Cement | 8.0 bags (50-kg) | bags/m³ |
| Washed Sand (FA) | 0.50 m³ | m³/m³ |
| 3/4" Gravel (CA) | 1.00 m³ | m³/m³ |

E. Mortar for CHB Laying – 1:3 Masonry Mortar

Standard mortar quantities for 6" CHB laying (per m² of wall):

| Component | Quantity | Unit |
| --- | --- | --- |
| Masonry Cement | 0.45 bags | bags/m² |
| Fine Sand | 0.035 m³ | m³/m² |

F. Plastering Mortar – 1:3 mix, 20mm thick (Both Sides)

| Component | Quantity | Unit |
| --- | --- | --- |
| Volume of plaster/side | Area × 0.020 m | m³ |
| Masonry Cement | 0.45 bags/m² | bags/m² |
| Fine Sand | 0.035 m³/m² | m³/m² |

G. Wage Rates & Employer Contributions

| Item | Skilled (₱/day) | Unskilled (₱/day) | Notes |
| --- | --- | --- | --- |
| Basic Daily Wage | ₱ 600.00 | ₱ 520.00 | Per assignment |
| SSS (Employer share) | ₱ 57.00 | ₱ 49.40 | 9.5% of wage |
| PhilHealth (Employer) | ₱ 25.00 | ₱ 21.67 | 5% / 2 × wage |
| Pag-IBIG (Employer) | ₱ 12.00 | ₱ 12.00 | ₱100/mo ÷ 25 days |
| TOTAL Daily Rate | ₱ 694.00 | ₱ 603.07 | All-in |

H. Productivity Rates (Based on Industry Practice)

| Work Item | Skilled | Unskilled | Output/Day |
| --- | --- | --- | --- |
| CHB Laying | 1 mason | 1 laborer | 8–10 m²/day per team |
| Concrete Pouring (Footing) | 1 mason | 2 laborers | 2–3 m³/day |
| Formwork Installation | 1 carpenter | 1 laborer | 10–12 m²/day |
| Plastering | 1 mason | 1 laborer | 10–12 m²/day per team |
| Rebar Installation | 1 ironworker | 1 laborer | 150–180 kg/day |

II. QUANTITY TAKE-OFF (QTO)

A. Basic Dimensions

| Element | Dimension | Computed Value |
| --- | --- | --- |
| Bay width (L) | 4.20 m | — |
| Wall height above NGL (H) | 2.40 m | — |
| Wall Area (gross, one span) | L × H | 4.20 × 2.40 = 10.08 m² |

B. Isolated Footing (FC1) Concrete Volume

Footing Size: 0.80 m × 1.30 m × 0.30 m

| Element | Formula | Value |
| --- | --- | --- |
| Footing Volume | 0.80 × 1.30 × 0.30 | = 0.312 m³ |
| No. of footings per span | 2 footings (one at each column) | 2 |
| Total Footing Volume | 0.312 × 2 | = 0.624 m³ |

C. Column Pedestal / Wall Below NGL

Assuming column size = 200mm × 200mm, from footing top to NGL = 600mm − 300mm (footing) = 300mm stub:

| Element | Formula | Value |
| --- | --- | --- |
| Column stub (below NGL) | 0.20 × 0.20 × 0.30 × 2 pcs | = 0.024 m³ |
| Column above NGL to Lintel | 0.20 × 0.20 × 2.20 × 2 pcs | = 0.176 m³ |
| Total Column Concrete | 0.024 + 0.176 | = 0.200 m³ |

D. Lintel Beam Concrete Volume

Lintel Beam: 150mm × 200mm × 4.20m (span, beam sits on top of CHB wall at apex)

| Element | Formula | Value |
| --- | --- | --- |
| Lintel Beam Volume | 0.15 × 0.20 × 4.20 | = 0.126 m³ |
| Total Lintel Beam Volume | — | = 0.126 m³ |

E. Summary – Total Concrete Volume

| Element | — | Volume (m³) |
| --- | --- | --- |
| Footings (2 pcs) |  | 0.624 |
| Columns |  | 0.200 |
| Lintel Beam |  | 0.126 |
| TOTAL CONCRETE |  | 0.950 m³ |

F. CHB Wall Area & Quantity

Net CHB Wall Area = Gross Wall Area − Lintel Beam area − Column areas

Lintel beam face area = 0.15m × 4.20m = 0.63 m² (deduct from one face, but for CHB count use net wall)

Column face areas = 0.20m × 2.40m × 2 = 0.96 m²

Net CHB Wall Area = 10.08 − 0.63 − 0.96 = 8.49 m²

| Element | Formula | Value |
| --- | --- | --- |
| Gross Wall Area | 4.20 × 2.40 | 10.08 m² |
| Deduct Lintel Beam | 0.15 × 4.20 | 0.63 m² |
| Deduct 2 Columns | 0.20 × 2.40 × 2 | 0.96 m² |
| Net CHB Wall Area | 10.08 − 0.63 − 0.96 | = 8.49 m² |

CHB Count: 6" CHB standard size = 150mm × 200mm × 400mm

Block face area = 0.20m × 0.40m = 0.08 m²/block

Blocks needed (net) = 8.49 / 0.08 = 106.13 ≈ 107 pcs

Add 5% wastage: 107 × 1.05 = 112.35 ≈ 113 pcs

| Item | Calculation | Qty |
| --- | --- | --- |
| Block face area | 0.20 × 0.40 | 0.08 m²/pc |
| Net blocks | 8.49 / 0.08 | 107 pcs |
| + 5% wastage | 107 × 1.05 | 112 pcs |
| TOTAL 6" CHB | round up | 113 pcs |

G. Mortar for CHB Laying (1:3 Masonry Mortar)

Masonry Cement: 0.45 bags/m²  |  Fine Sand: 0.035 m³/m²  (for 6" CHB, 10mm joints)

| Material | Formula | Qty |
| --- | --- | --- |
| Masonry Cement (net) | 8.49 × 0.45 | 3.82 bags |
| + 10% wastage | 3.82 × 1.10 | 4.20 bags → 5 bags |
| Fine Sand (net) | 8.49 × 0.035 | 0.297 m³ |
| + 10% wastage | 0.297 × 1.10 | 0.327 m³ |

H. Plastering Mortar – 20mm thick, Both Sides (1:3)

Plaster applied to both faces of CHB wall: 2 × 8.49 m² = 16.98 m²

Volume of plaster = 16.98 × 0.020m = 0.340 m³

Using 1:3 ratio — Cement content ≈ 9.0 bags/m³, Sand ≈ 0.96 m³/m³ of plaster

| Material | Formula | Qty |
| --- | --- | --- |
| Plaster area (both sides) | 2 × 8.49 | 16.98 m² |
| Plaster volume | 16.98 × 0.020 | 0.340 m³ |
| Masonry Cement (net) | 0.340 × 9.0 | 3.06 bags |
| + 10% wastage | 3.06 × 1.10 | 3.37 → 4 bags |
| Fine Sand (net) | 0.340 × 0.96 | 0.326 m³ |
| + 10% wastage | 0.326 × 1.10 | 0.359 m³ |

I. Concrete Materials – Footings, Columns, Lintel (1:2:3 Site Mix)

Total concrete = 0.950 m³. Add 10% wastage = 0.950 × 1.10 = 1.045 m³

Per m³: Cement = 8.0 bags, Washed Sand = 0.50 m³, 3/4" Gravel = 1.00 m³

| Material | Formula | Qty |
| --- | --- | --- |
| Portland Cement | 1.045 × 8.0 | 8.36 → 9 bags |
| Washed Sand | 1.045 × 0.50 | 0.523 m³ |
| 3/4" Gravel | 1.045 × 1.00 | 1.045 m³ |

J. Reinforcing Steel

Footing (FC1): 7-12mm dia. (X-axis) + 5-12mm dia. (Y-axis), Embedment=600mm

| Bar Location | Count | Length (m) | Total (m) |
| --- | --- | --- | --- |
| Footing X-bars (7-12d, per ftg) | 7 | 0.80−0.075 = 0.725 | 5.075 × 2 ftg = 10.15 |
| Footing Y-bars (5-12d, per ftg) | 5 | 1.30−0.075 = 1.225 | 6.125 × 2 ftg = 12.25 |
| Column Vert. Bars (4-12d) | 4 | 0.60+2.40+0.20 = 3.20 | 3.20 × 4 × 2 col = 25.60 |
| Column Ties (10d @150 O.C.) | (2.40/0.15)+1=17 | 4×(0.20−0.025)×2 = 0.70 | 17 × 0.70 × 2 = 23.80 |
| Lintel Beam (4-12d) | 4 | 4.20 + 0.30 = 4.50 | 4.50 × 4 = 18.00 |
| Lintel Stirrups (10d @200) | (4.20/0.20)+1=22 | 2×(0.15+0.20)×2 = 0.70 | 22 × 0.70 = 15.40 |
| Total 12mm dia. bars |  |  | 66.00 m |
| Total 10mm dia. bars |  |  | 39.20 m |

12mm bar weight: 0.888 kg/m × 66.0 × 1.10 = 64.41 kg

10mm bar weight: 0.617 kg/m × 39.2 × 1.10 = 26.59 kg

→ 12mm rebars: 64.41 kg ÷ 9 m/bar × 0.888 kg/m = approx 8 pcs (9m bars)

→ 10mm rebars: 26.59 kg ÷ 9 m/bar × 0.617 kg/m = approx 5 pcs (9m bars)

K. Formworks

Forms needed for: Footing sides + Column sides + Lintel beam sides/bottom

| Element | Form Area (m²) | Notes |
| --- | --- | --- |
| Footing (4 sides × 2 ftg) | 2×(0.80+1.30)×2×0.30 = 2.52 | sides only |
| Columns (4 sides × 2 col) | 4×0.20×2.40×2 = 3.84 | above NGL |
| Lintel Beam (3 sides) | 2×0.20×4.20+0.15×4.20 = 2.31 | sides+bottom |
| Total Form Area |  | 8.67 m² |

Phenolic Board: 8.67 / 4 (re-use) = 2.17 m² → 2.17/2.44² sheet = 0.36 sheets → 1 sheet of 3/4" Phenolic

Good Lumber (2"×2"×8'): For form support, estimate 4 bd.ft. per m² of form = 8.67 × 4 / 4 (reuse) = 8.67 bd.ft. → 9 bd.ft.

III. MATERIAL COST ESTIMATE PER SPAN/BAY

| Material Description | Qty | Unit | Unit Price (₱) | Amount (₱) | Remarks |
| --- | --- | --- | --- | --- | --- |
| A. CONCRETE WORKS (Footings, Columns, Lintel Beam) |  |  |  |  |  |
| Portland Cement (3000psi concrete) | 9 | bags | 250.00 | 2,250.00 | 1:2:3 mix |
| Washed Sand | 0.523 | m³ | 1,800.00 | 941.40 |  |
| 3/4" Gravel | 1.045 | m³ | 1,900.00 | 1,985.50 |  |
| Sub-total – Concrete |  |  |  | 5,176.90 |  |
| B. REINFORCING STEEL |  |  |  |  |  |
| 12mm dia. deformed bars (9m) | 8 | pcs | 280.00 | 2,240.00 | ~₱280/pc market price |
| 10mm dia. deformed bars (9m) | 5 | pcs | 180.00 | 900.00 | ~₱180/pc market price |
| Tie Wire (G.I. wire #16) | 2 | kg | 75.00 | 150.00 | market price |
| Sub-total – Rebar |  |  |  | 3,290.00 |  |
| C. FORMWORKS (with Re-use Factor = 4) |  |  |  |  |  |
| 3/4" Phenolic Board | 1 | sheet | 2,200.00 | 550.00 | ÷ 4 re-use |
| 2"×2"×8' Good Lumber | 9 | bd.ft. | 90.00 | 202.50 | ÷ 4 re-use |
| Common Wire Nails (Assorted) | 0.5 | kg | 80.00 | 40.00 | market price |
| Sub-total – Formworks |  |  |  | 792.50 |  |
| D. CHB WALL LAYING |  |  |  |  |  |
| 6" CHB | 113 | pcs | 25.00 | 2,825.00 | +5% wastage |
| Masonry Cement (CHB mortar) | 5 | bags | 180.00 | 900.00 | 1:3 mix |
| Fine Sand (CHB mortar) | 0.327 | m³ | 2,100.00 | 686.70 |  |
| Sub-total – CHB Wall |  |  |  | 4,411.70 |  |
| E. PLASTERING (20mm, Both Sides) |  |  |  |  |  |
| Masonry Cement (plaster) | 4 | bags | 180.00 | 720.00 | 1:3 mix |
| Fine Sand (plaster) | 0.359 | m³ | 2,100.00 | 753.90 |  |
| Sub-total – Plastering |  |  |  | 1,473.90 |  |
| TOTAL MATERIAL COST PER SPAN/BAY |  |  |  | ₱ 15,145.00 |  |

IV. LABOR COST ESTIMATE PER SPAN/BAY

A. Wage Rates (All-in Daily Rates with Employer Contributions)

| Worker Type | Basic (₱) | SSS (₱) | PhilHealth+PAGIBIG (₱) | All-in (₱) |
| --- | --- | --- | --- | --- |
| Skilled Worker (Mason/Carpenter) | 600.00 | 57.00 | 37.00 | 694.00 |
| Unskilled Worker (Laborer) | 520.00 | 49.40 | 33.67 | 603.07 |

B. Labor Cost Computation by Work Item

| Work Item | Quantity | Prod. Rate | Days Req. | Skilled | Unskilled | Total (₱) |
| --- | --- | --- | --- | --- | --- | --- |
| 1. Formwork Installation |  |  |  |  |  |  |
| Form Area = 8.67 m² Prod = 10 m²/day/team Days = 8.67/10 = 0.87 day | 8.67 m² | 10 m²/day | 0.87 | 1 Carpenter 0.87 × ₱694 = ₱603.78 | 1 Laborer 0.87 × ₱603.07 = ₱524.67 | ₱1,128.45 |
| 2. Concrete Pouring (Footings + Columns + Lintel) |  |  |  |  |  |  |
| Volume = 0.950 m³ Prod = 2 m³/day/team Days = 0.475 day | 0.950 m³ | 2 m³/day | 0.48 | 1 Mason 0.48 × ₱694 = ₱333.12 | 2 Laborers 0.48 × 2 × ₱603.07 = ₱578.95 | ₱912.07 |
| 3. Rebar Installation |  |  |  |  |  |  |
| Steel = 91 kg total Prod = 150 kg/day/team Days = 0.61 day | 91 kg | 150 kg/day | 0.61 | 1 Ironworker 0.61 × ₱694 = ₱423.34 | 1 Laborer 0.61 × ₱603.07 = ₱367.87 | ₱791.21 |
| 4. CHB Laying |  |  |  |  |  |  |
| Area = 8.49 m² Prod = 8 m²/day/team Days = 1.06 days | 8.49 m² | 8 m²/day | 1.06 | 1 Mason 1.06 × ₱694 = ₱735.64 | 1 Laborer 1.06 × ₱603.07 = ₱639.25 | ₱1,374.89 |
| 5. Plastering (Both Sides) |  |  |  |  |  |  |
| Area = 16.98 m² Prod = 10 m²/day/team Days = 1.70 days | 16.98 m² | 10 m²/day | 1.70 | 1 Mason 1.70 × ₱694 = ₱1,179.80 | 1 Laborer 1.70 × ₱603.07 = ₱1,025.22 | ₱2,205.02 |
| TOTAL LABOR COST PER SPAN/BAY |  |  |  |  |  | ₱ 6,411.64 |

V. COST SUMMARY PER SPAN/BAY

| Item | Description | Cost (₱) |
| --- | --- | --- |
| A | Concrete Works (Materials) | ₱ 5,176.90 |
| B | Reinforcing Steel (Materials) | ₱ 3,290.00 |
| C | Formworks (Materials, with re-use factor=4) | ₱ 792.50 |
| D | CHB Wall – 6" CHB + Mortar (Materials) | ₱ 4,411.70 |
| E | Plastering 20mm both sides (Materials) | ₱ 1,473.90 |
| TOTAL MATERIAL COST |  | ₱ 15,145.00 |
| 1 | Labor – Formwork | ₱ 1,128.45 |
| 2 | Labor – Concrete Pouring | ₱ 912.07 |
| 3 | Labor – Rebar Installation | ₱ 791.21 |
| 4 | Labor – CHB Laying | ₱ 1,374.89 |
| 5 | Labor – Plastering | ₱ 2,205.02 |
| TOTAL LABOR COST |  | ₱ 6,411.64 |
| GRAND TOTAL COST PER SPAN/BAY |  | ₱ 21,556.64 |

VI. NOTES & REFERENCES

1. Structural dimensions taken from Drawing S-2 (Elevation View and Footing Schedule).

2. Rebar prices (12mm, 10mm) based on current market rates (approx. ₱280/pc and ₱180/pc for 9m bars).

3. Tie wire price based on current hardware market (~₱75/kg).

4. Nails price based on current hardware market (~₱80/kg).

5. Employer contributions: SSS (9.5%), PhilHealth (5% split), Pag-IBIG (₱100/month ≈ ₱4/day).

6. Productivity rates sourced from DPWH guidelines and interview-based field norms.

7. Mix design ratios from DPWH Blue Book standard proportions (1:2:3 = 8 bags cement, 0.50 m³ sand, 1.00 m³ gravel per m³ concrete).

8. Mortar quantities for CHB laying: 0.45 bags masonry cement + 0.035 m³ fine sand per m² (standard 6" CHB, 10mm joint).

9. Plastering mortar: 1:3 ratio, 20mm thick on both faces; 9 bags masonry cement and 0.96 m³ sand per m³ of plaster.

10. Excavation and earthworks excluded per Assignment specification Item 7.